## Risk Worksheet
Risk Assessment Worksheet for Food Truck Information System
|  | Reviewed by: | Faiza Busera
Source Person: | Shouq Alamer | Date entered into Risk Register: | 2019-03-31
Date Submitted: | 2019-04-02 | Risk ID Number: | FTIS-2019
1. Risk ID Date: | 2019-04-01 | 6. Impact: |  | 2
| The date the risk was identified | 1 = Low (Minor Impact) 2 = Medium (Significant Impact) 3 = High (Major Impact)
2. Risk Title: |  | 7. Probability: |  | 2
1 = <30% 2 = 30% - 70% 3 = >70%
Natural Disaster as risk for Food Truck Information System
|  | 8. Risk Exposure (RE): |  | 4
3- 6 words description which captures the major concern |  | The product of the Impact x Probability
3. Risk Statement: |  | 9. Timeframe: |  | <30
Days in which the risk migh occur
Natural disasters are common such as hail, snow, lightning, heavy rainfall, and wind disturbances all pose a major threat to food truck Information system.
10. Other Comments:
4. Risk Owner: | Shouq Alamer
Person responsible for managing this risk
5. Risk Category: | Ease of Use
RISK ACTION PLAN
11. Risk Mitigation Steps:
Description |  | Responsible Person | Due Date
1. Develop strategies to operate in natural disaster |  | Pratima Bhattarai | 2019-04-15
2.Update and maintain current maps of areas within the city which faces more natural disasters. |  | Shouq Alamer | 2019-04-15
3. Delivering Food in wraps |  | Faiza Busera | 2019-04-15
4. Sending delivery early to save time. |  | Faiza Busera | 2019-04-15
12. Contingency Plan:
Description |  | Person Responsible | Event
1.Immediately call 911 and notify the authorities of the situation. |  | Pratima Bhattarai | 2019-04-20
2.All personnel are to evacuate the premises and gather at the emergency meeting area so that they can be accounted for |  | Shouq Alamer | 2019-04-20
3.Critical data is regularly backed up to secure data |  | Faiza Busera | 2019-04-20
4. If a disaster that will render the server unserviceable is imminent, data on the server should be immediately backed up to the server room hard drives and the hard drives should be removed and stored off-premises. |  | Shouq Alamer | 2019-04-20
Note on A37: List steps/actions recommended to mitigate risk.
Note on D37: List a person for each step/action.
Note on E37: When should the person complete assigned step.
Note on A45: List steps/actions recommended to mitigate risk.
Note on D45: List a person for each step/action.
Note on E45: Trigger event which will prompt contingency plan implementation.

## DropDowns
Value | Impact | Probability | Timeframe | Risk Status | Risk Categories
1 | Low | <30% | <30 | Open | Business
2 | Medium | 30% - 70% | 30-90 | Closed | Contract
3 | High | >70% | >90 | Retired | Data/Information
|  |  |  | Transferred | Depend and Inter-operability
Ease of Use
Feasibility
Initial Cost
Investment Mgmt Capability
Life-Cycle Costs
Monopoly for Future Procur
Org and Change Mgmt
Personnel Skill
Policy Compliance
Political
Privacy
Project Resources
Reliability of System
Requirements
Risk of Project Failure
Schedule
Security
Standards
Strategic
Surety
Technical Obsolescence
Technology

## Risk Categories Definitions
Risk Category Definitions
Business Risk – is the likelihood that the project will fail to achieve operational goals due to the nature of the business itself may change or the underlining policies effecting the effectiveness of the solution. Example: Reliance on congressional approval for the continued funding of programs.
Data/Information Risk – is the likelihood that solution implementation will result in loss/misuse of data or information, and/or will increase burdens on citizens and businesses due to data additional data collection requirements. Alternatively, it is the risk that the data conversion will be more challenging then planned. Example: The migration of data to a target system may require additional preparation and cleanup effort beyond what was originally planned.
Dependency and Interoperability Risk – addresses the environment in which the project is being developed and in which the system will operate. Dependency Risk is the likelihood that the implementing organization will not receive intended benefits from the project due to its dependency upon another organization or project for delivery of critical project elements or project risk control elements. Interoperability Risk is the likelihood that the intended solution will not interact well with other systems of the Agency or external organizations lack of familiarity with and completeness of the interfaces, and immaturity of the service exchange concept among different solutions.
Feasibility Risk – is the likelihood that the technical and economic challenges will render the intended solution impractical to develop. Example: The required infrastructure may not be able to support the solution provided by the system software.
Initial Cost Risk – is the likelihood that the actual initial or acquisition cost of the project may be more than the budgeted cost due to inaccuracy of the cost estimate resulting from inadequate cost estimation methods, incomplete or inaccurate data, and lack of clarity in project scope. Example: The costs for a system deployment may exceed initial budget forecasts.
Investment Management Risk – is the likelihood that the solution will prove too complex for the Agency to manage itself (e.g., a high number of sub-tasks and/or number of performing organizations). This will necessitate obtaining and using applicable resources and activities that may be outside of the Agency’s control.
Life-Cycle Costs Risk – is the likelihood that total acquisition, operation and maintenance, and retirement costs of a project may be higher than estimated due to the difficulty involved in forecasting future events affecting the costs. Example: The operating cost to maintain a deployed system in the field may exceed initial budget forecast.
Monopoly for Future Procurements Risk – is the likelihood that the maintenance and upgrade services to the solution being acquired will, in the future, be available from one source only. This exclusivity may be due to use of proprietary platforms, market dominance, patent or intellectual property protection, or lack of adequate documentation; forcing the Agency to acquire other solutions from a single (or limited) vendor, thereby precluding future competition for system upgrades or modifications.
Organization/Change Management Risk – is the likelihood that the organizational/agency/government-wide cultural resistance to change and standardization, tendency to bypass required organizational changes, lack of use or improper use or adherence to new systems and processes, and inadequate training planning will result in organizational friction, resulting in implementation difficulty. Example: The OPG may encounter resistance by projects to use established procedures to manage projects.
Privacy Risk – is likelihood that a solution will be unable to protect confidential personal or sensitive non-government information from being accessed by unauthorized persons and that information stored in it will be subject to criminal/fraudulent misuse by those with authorized or unauthorized access. Example: A security plan is not developed for the deployment of a system overseas containing sensitive data.
Project Resources Risk – the likelihood that necessary resources will not be available in time or that the required knowledge/skills will not be available when needed. Example: Resources needed to support a CMMI level 3 assessement are not available during planned implementation.
Reliability of System Risk – is the likelihood that the intended solution will prove prone to failure, difficult or expensive to maintain and operate, and not capable of optimally delivering the intended functionality in accordance with prescribed requirements. Example: A proposed system or tool may not support the technical requirements of USAID.
Risk of Project Failure – is the likelihood that a project or program will not succeed or meet its intended objectives as planned. Project failure may stem from a combination of factors (i.e. financial instability, poor documentation, overly optimistic schedules, no established project guidelines, no established measures of accomplishment) which, if left unchecked, could threaten the success of the overall project or program. Example: There is a lack of endorsement, support, and participation of project management in the policies and standards established by the the OPG.
Schedule Risk – is the likelihood that the project will not be completed within the specified schedule. Alternatively, the planned project schedule is inadequate so as not to allow sufficient time for all required tasks to be completed within planned schedule. Example: An aggressive project schedule contains no built-in slack time.
Security Risk – is the likelihood that the solution will be vulnerable to unauthorized intrusions and damage or will be connected with or dependent on other such vulnerable systems, networks and databases and will fail to protect itself from outside interference. Example: A web-based application deployed overseas does not contain sufficient safeguards to prevent unauthorized access via the internet.
Strategic Risk – is the likelihood that the project will not support the agency’s strategic or government-wide goals. This failure fail to achieve or inadequately contribute to their achievement may be due to competing or conflicting objectives of various stakeholders supporting the development and operation of the project. Example: Project goals due not support or are in conflict with the mission goals of the USAID Business Transformation Executive Committee.
Surety Risk – is the likelihood that project and program assets are protected against unauthorized use, modification, or deletion. Example: Established procedures are not in place to authorize access and changes to project or program assets.
Technology Risk – is the likelihood that the new development of the new solution or expansion of an existing one will fail to provide a greater level of performance than previously demonstrated, will fail to achieve an existing level of performance due to new constraints or will fail to operate as designed. Example: Existing bandwidth may not support transaction processing requirements of a proposed telecommunication system.
Technical Obsolescence Risk – is the likelihood that the performance levels obtained from the technology used in the project will yield less benefit than technologies available soon after the project is completed.